## Risk Register
Risk Register
Project: | Amgent Wealth Management Cybersecurity Upgrade
Prepared by: | Ksheetij Sirmal (CIHE250202)
Risk | Impact | Likelihood | Owner | Control / Mitigation
DNS migration causes email outage | High | Medium | Sankosh | Export and verify DNS before change
Conditional Access locks out users | High | Medium | Prabesh | Use pilot group and emergency admin
Intune policy disrupts laptop | High | Medium | Sushil | Test-device deployment first
Defender blocks business application | Medium | Medium | Kiran | Pilot policy and review exclusions
DLP blocks valid file sharing | Medium | Medium | Ksheetij | Test policy before enforcement
Password or secret exposed in GitHub | High | Low | All | Secret-review process; never upload credentials
Missing project evidence | Medium | Medium | All | Evidence register and naming rules
Incorrect SharePoint/OneDrive permissions | High | Low | Ksheetij | Document current state and validate changes before enforcement